## ROW HOUSES - A
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR ROW HOUSES 'A'
Sl.No | Point | Without Financial Effect | With Financial Effect | Not Feasible | Remarks
1 | The toilet at GF should have a common door from the common area in addition to the opening from the bed rooms. |  |  | Not Feasible
2 | Kitchen needs additional loft with sliding doors. |  |  | Not Feasible | Provision for modular kitchen is provided
3 | The bed room needs additional loft for storage. | considered |  |  | Possible in first floor Bed rooms no.2
4 | The WC in the toilet should be spaced away from the wall. (Presently the gap between the WC and the wall is less than 5 inches.­ | considered
5 | Possibility of having Solar Heater for each house to be explored. |  | Possible for 150 liters capacity, Additional cost approx Rs.35000/Unit
6 | Installation provision for AC (Box AC + Spilt AC) is in the bed room. |  |  |  | Split AC provision exists
7 | Small loft tanks (10 Ltrs Capacity) in the kitchen | Not Considered
8 | The common area in the first floor should have a uniform floor (Presently the floor is stepped near the exit to balcony) | Considered
9 | Collective permission from the “Town Planning Corporation” may be taken for future augmentation by owners, in terms of a second floor replica of first floor and or additional rooms(s) in the terrace(s) |  |  | Not Feasible | Approval from DTCP Chennai is to be obtained, subject to local bye-laws.
10 | Provision to construct an additional curving staircase to the terrace / Second floor may be made available in terms of a soft roof. |  | considered MS Ladder provided to access the terrace approx Rs 10000/ per unit
11 | The present staircase is dangerous for children. The short hand rail on the right, while climbing up, has wide gaps in between hand rail through which a child can slip through and fall. | considered |  |  | Change of staircase design is already forwarded to all allottees for opinion.
12 | Front Elevation. The top sun shade being rectangular in shape and does not match with bay window shape. Its shape also to be same as that of window. |  |  | Not Feasible | The detail provided at site is appropriate
13 | Between the top tiled roof and the sun shade there is a gap which needs to be closed. | considered
14 | The tiled roof ends up very close to the window. The rain water will splash in the hall. | considered
15 | There is no provision for storage utility items in Bath Room. |  |  | Not Feasible
16 | Wall tiles are to be a lighter colour. (Toilet) | considered
17 | First floor exist to the balcony, the sun shade is too small. Rain water will spill over the surface. The toilet room can be extended to the door also. | considered
18 | The platform made near the steps needs to be removed. | considered
19 | Provision required for a screen to isolate wet area and dry area in bath room | Not Considered
20 | Parapets wall in the terrace is too high for a sit out. | considered
21 | Avoid difference of height in the floor level at stairs landing at first floor | Considered
22 | Car Parking/Garage is too small it needs to be increased. | Considered
23 | Kitchen may be fitted with deeper twin basin |  | additional cost Rs.2000/ Sink.
24 | Wash area next to kitchen not enclosed. It should be widened | Will be enclosed up to parapet ht. |  |  | Adequate space provided
25 | Loft slabs may be reduce to 50 mm thickness | Considered
26 | There was a door provided in the earlier drawing towards backyard under stair case which is blocked now. |  |  |  | The revision does not facilitate the same.
27 | Remove the platform from the top hall towards balcony. Make it stopping to avoid accidents | Considered
28 | Main door is exposed to rain and sun. Needs to have portico type coverage to an appropriate length. | Considered
29 | Spiral Stair Case /Curving stair case has eaten up a lot of space. A lot of waste of space at the landing area at bottom and top. Spiral Stair Case steps have uneven width. Provide straight landing stair case | considered |  |  | Change of staircase design is already forwarded to all allottees for opinion.
30 | Exhaust hole for chimney in Kitchen to be provided |  |  |  | Provision already exists.
31 | Staircase hand railing at the edge to give more space. Increase the size of steps. Nosing more by one inch. | considered
32 | Power backup required |  | Additional cost for 0.5 KVA- approx Rs.15000/- Perunit or flat |  | Provision for UPS already exists for individual flats, Generator supply for common area, lifts etc.
33 | UPVC material consider as announced may be provided for better finish. |  |  |  | Sample approved by AFNHB is provided.
34 | Fans to be put in centre of room as people can have the option of keeping cots wherever they please. | Considered |  |  | Presently placed as per the Furniture layout
35 | First floor bed room size can be increased by reducing the common space | Considered
36 | provision of electrical point and water connection for washing machine to be provided |  |  |  | Provision is already exists
37 | RO water source should be provided on the right side of kitchen wall near sink. |  |  |  | Provision already exists
38 | Kitchen slab should have a gas pipe hole. |  |  |  | Provision already exists
39 | Double height sun windows should have opaque glass. It will have a dual purpose:- (i) No curtains can be made there, opaque glass will provide privacy. (ii) Outside lentil area will not be visible. | considered |  |  | Provision already exists; translucent glass which will blur the vision only will be provided.
40 | Master bedroom dressing room loft not feasible as beam is obstructing. | Considered
41 | Grill door for entrance and service entrance |  | Appox cost Rs.6000/- Each |  | Since the main door is steel no grill door is required. Rear service verandah may be provided with grill and grill door for safety purpose if required with additional cost.
42 | Kitchen wall with the slab service opening can be knocked down. It will make the kitchen bigger and the service counter can double up as breakfast table |  |  | Not Feasible
43 | The granite at Kitchen may be black in colour. |  |  |  | Present proposed cats eye granite is expensive than the black granite.
44 | Provision for Hooks for Jula may be given in living room |  | Per hook will costs approx Rs.500/-
45 | The entire area around the house to be with Paver block |  | Addition cost Rs18000/ per unit
46 | Grill doors to be incorporated in addition to the sliding glass doors in the first floor, bed room to balcony. |  |  | Technically not feasible
47 | Height of the washbasin to be increased to the standard height | Considered
48 | Provision of two to three inches holes for fitment of split air conditioners must be catered in all rooms. | Not Considered |  |  | Suitable hole may be done by the A/C supplier during the Installation
49 | Quality of door is not good. (Shrinkage/bulging noticed in one of the doors). Good quality doors required. change the doors facing the weather | considered |  |  | Steel door provided as a replacement.
50 | Front Elevation.Top toilet window and exhaust hole needs to be shifted to side instead of front side. |  |  | Not Feasible
51 | Colour of bathroom may be of light colour. | considered
52 | Instead of four small windows on the semi circular wall, 1 or all shutter windows may be planned on the straightened wall. | As spiral staircase is changing a suitably modification is done to the windows too.
53 | Kitchen shelf/cabinets platform is of 100 mm thickness. This may be reduced to the least possible thickness and not more than 50 mm finished thickness, to permit maximum utilization of space. | Considered
54 | Kitchen geyser and water purifier positions may be shifted to more practical locations. |  |  |  | Fixed at appropriate place
55 | All windows including kitchen window and doors opening outwards may be provided with mosquito proofing |  |  |  | Provision already exists Except Kitchen Window
56 | Grills may be of specifications in the plan (Gauge, spacing, shape -round/square/flat- etc. | Considered
57 | Electrical switch points, AC, TV, telephone points need to be re located with probable bed positions. | Considered
58 | All items including the floor and wall tiles should be of approved brand | Considered |  |  | Sample approved by AFNHB is provided
59 | Colour and colour combinations of tiles, especially the wall tiles needs to be changed and standardized. | Considered
60 | The Tracks of the French Door/ window to be flushed with the floor. A stepping down of the terrace outside with proper slope and large size rain water drain pipes to ensure easy flow of water would ensure that water does not seep in through the sill area. |  |  |  | Provision is already exists
61 | As per the original plan, door to be provided from kitchen to work area | considered

## ROW HOUSES -B
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR ROW HOUSES 'B'
Sl.No | Point | Without Financial Effect | With Financial Effect | Not Feasible | Remarks
1 | An option for changing one closet to Indian Style in the toilet and an option may be given for changing the tiles into marbles for living room, at extra charge. | Not considered
2 | Hooks for Cradles required for all rooms. | considered | Rs.500/-per cradle Hook
3 | Putty work to be carried out for ceiling also. |  |  |  | Provision already exists only for living and dinning area
| Wash basin position to be changed to hall side wall and closet to be shifted towards one corner | Not considered
5 | Sink size to be changed. Present one is very small | Considered |  |  | Kitchen size increased.
6 | Shelf can be changed to marble or granite. |  |  |  | Polished cuddapah slab is existing for shelf, Marble/Granite may add up the cost.
7 | Kitchen platform must be minimum 28” to accommodate gas cylinder. | Considered
8 | Dining the open space for ventilator may be changed. | Considered
9 | Bed Room toilet door location to be changed. It can be shifted to outside hall area. So that utility of toilet will be better. |  |  | Not Feasible | due to provision of Counter Top basin
10 | House front side wall (bottom side of stair case) can be removed in order to increase space. | Considered
11 | There is a door and window at the OTS near the dining place. Instead of the window the wall can be covered and a French window may be provided in place of door | Considered
12 | The closet in the attached toilet is nearer to the wall. The position please be changed for easy access for all sizes of persons | Considered
13 | Night lamp in bedroom to be shifted near to ward robe area | Considered
14 | There should be a provision of small shelf in Toilets |  |  | Not Feasible
15 | There is a requirement of widening the end of the stair case nearing upstairs as it is very narrow | Considered
16 | Position the water tank over the top elevation or the place covered by the top elevation |  |  | Not feasible | It will affect the plumbing line
17 | Showcase in the hall may be provided | Considered
18 | Terrace floor should be made even | Considered
19 | Provision for big loft by bifurcating the height of the common toilet may be provided. |  |  | Not feasible | Due to height limitations
20 | Kitchen is very small, the size may be increased | Considered
21 | Hall can be extended since there is no division for dining and placing the TV | Considered
22 | There is no place for parking the vehicles | Considered |  |  | Suitable Modification done
23 | UPS wiring needs to be done for Power Back up |  |  |  | Provision already exists
24 | Granite sink to be provided in the kitchen |  |  | Not Feasible | Stainless steel sink only is provided
25 | Overhead water tank may be placed at south west corner(Vaastu) which also save space in the center for any function |  |  | Not Feasible | Vastu for colony as a hole has been considered, individual Du vastu cannot be addressed.
26 | Wash basin may be provided in the dining area. | Not considered
27 | Open space outside kitchen may be provided with sufficient plug points for washing machine and grinder etc. |  |  |  | Provision already Exist
28 | Shower fitted in the attached bathroom may be shifted from centre to the corner and wash basin be shifted to centre | considered
29 | A grill door (for safety reason) may be provided in the main door & back door |  | Appox cost Rs.12000/- Each |  | Since the main door is steel no grill door is required. Rear service verandah may be provided with grill and grill door for safety purpose if required with additional cost.
30 | Black colour tiles should not be used. Instead non-skid light coloured tiles may be used in the bathrooms/Toilet | considered
31 | Non skid tiles should be used |  |  |  | Provision already exists
32 | Tiles of the stair case are of old fashion and not appropriate. Tiles should be pasted on the walls of the kitchen. | considered
33 | If possible, door of the attached bathroom may be shifted to the wall at the front. | Considered
34 | One Magic Eye may be provided in the main door |  |  |  | Provision is already exists
35 | The point provided for drinking water to be near the washbasin so that it can be used for other purposes also |  |  |  | Provision is already exists
36 | Window AC provision to be provided. |  |  | Window A/c Not possible in the present window | Split A/c Provision already exists
37 | Wire mesh (Mosquito) in UPVC |  |  |  | Provision already Exists, Except kitchen window
38 | Solar water heater provision |  | Possible for 150 liters capacity, Additional cost appro Rs.35000/ Unit

## TYPE -A
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR TYPE 'A-I'
Sl.No | Point | Without Financial Effect | With Financial Effect | Not Feasible | Remarks
1 | Tiles on bathroom walls are up to 5 feet. Beyond this maintenance will be difficult in long run the ht may be reduced |  |  | Not Feasible
2 | Wash basins be positioned to the corners rather than right opposite to WC | Considered
3 | Provision for mirror fittings in bathroom | Not considered |  |  | There is wide choice for allottees in the Market.
4 | Toilet WC may be mounted on the wall for more complete and efficient cleaning and move it to one corner. | Considered
5 | Geyser not to be situated above the WC. | Considered
6 | Exhaust fan needs to be provisioned. |  |  |  | provision is already exists
7 | Four- 5Amps power sockets need to be provisioned in kitchen. |  |  |  | 2-15Amp, 3-5amp socket is already exists.
8 | Place for gas cylinder be provisioned |  |  |  | provision already exists
9 | Provision for Chimney exhaust is required. | Considered.
10 | Kitchen to be made more spacious | considered
11 | Space for fridge is very small. | considered
12 | Washing in kitchen can be shifted to balcony side. |  |  |  | Provision already exists
13 | L shaped platform in Kitchen should be increased | considered
14 | One more fan point to be provisioned in master bed room. |  |  | Not Feasible
15 | The provision for ceiling fans is not located correctly in the 2nd and 3rd bedroom. | considered
16 | Please consider enlarging the master bedroom balcony to include the wide full windows area outside |  |  | Not Feasible | Due to Govt. approval and sanction limitation.
17 | Change TV cable point and switch board in Master bed room at appropriate location. | considered
18 | Height of window in master bed room to be reduced. | Not considered |  |  | More allottees have preferred present position
19 | Space for bigger dining table required. Dining room space to be extended into balcony area. |  |  | Not Feasible | Due to Govt sanction and approval limitation
20 | Dining room window to be made into a sliding door. | considered
21 | No place for cutlery in dining room. | Considered
22 | Quality of doors and hinges need to be improved | considered
23 | The drawing room can be extended by displacing the window. |  |  | Not feasible | Due to Govt sanction limitation
24 | Window mosquito mesh. | . |  |  | provision is already exists except kitchen window
25 | Provision for fitment for curtains needs to be given as the walls do not have normal bricks but hollow bricks |  |  |  | (Solid blocks only used) not with hollow Bricks. curtain fitment is individuals choice
26 | Every switch board should have a plug point. |  |  |  | provision is already exists
27 | Entry of the house the sliding doors to study room is not secure needs to be changed | considered |  |  | It is a Solid PVC door as per contract
28 | Provision of window A/c to be provided |  |  |  | No provision for window A/C in the UPVC window. Split AC provision is only made
29 | Common toilet may have an additional door from the bed room |  |  | Not feasible
30 | Standard paint scheme should implemented. | considered
31 | The door lock in the rooms needs to be changed to different type with handle so that it is easy for operation with children in the house. | considered
32 | Switch board position in study and master bed rooms to be changed to some other place as one cannot have wardrobe. | Considered.
33 | Cable point in every bed room and drawing room is provided. |  |  |  | Provision is already exists
34 | Entrance foyer, slab to be fitted for shoe rack. |  |  |  | Provision is already exists
35 | Big loft outside the french windows near the drawing-cum-dining room to be made accessed from outside |  |  | Not Feasible | Due to Structural limitations.
36 | Provide depression into the wall of study room to cater for show case in dining-cum-drawing room. | considered
37 | POP decorations in drawing room not required. |  |  |  | Simpler POP detail provided as per the drawing
38 | Height of plug points to be raised | considered
39 | Provide CFL holders/bulb holders in each room. Tube light concept is old fashion. |  |  |  | Electrical fittings and fixture are allottees choice.
40 | UPS wiring to be provided in hall, dining, bed and kitchen for individual flats. |  |  |  | Already provision exists
41 | Floor wise water distribution and connection for one indoor water tank in each flat may be provided. | Not considered |  |  | Its individuals choice
42 | Storm water drain should be provided for each house. |  |  |  | Already provisioned
43 | Collapsible grill door to be provided for each entrance of the flat for security reasons. |  |  |  | The main door is steel no grill door is required.
44 | Two 15 amp point must be in the dining area.(one for fridge + one for any other appliance) |  |  |  | Any model fridge 5 Amps plug is sufficient,
45 | The balcony tiles should be the same tiles as inside as the terracotta tiles colour fades and water stains are visible | considered
46 | Since one cannot fix any clothes hanger/stand in the bathroom door due to the ABS doors. Powder coated aluminum clothes stand which costs anywhere between (Rs.75-150) may be fixed. |  |  |  | Refer Sl no -3
47 | In the 3rd bedroom /bathroom the washbasin should be in one corner |  |  | Not Feasible | Difficult to isolate the dry area and wet areas
48 | Sliding windows actually reduce the space for air flow. This is applicable for all rooms. |  |  | Not Feasible | All the rooms have adequate cross ventilation, if openable windows are opted; provision for fly proof shutter is a problem as it is already provisioned in the sliding window.
49 | With 7 entrances from Dining Hall around, the space dining room inside is negligible for movement of people particularly when the Dining Table & chairs are put. |  |  |  | it is sufficient to accommodate the furniture’s as indicated in the drawing.
50 | Entrance to the verandah behind the Dining hall is only through one of the bed room. There is no provision for going to the verandah from the Dining hall or Drawing Room. | considered
51 | There is no provision for putting a cub-board for keeping the crockery/cutlery since the space available is less in the dining hall area. Also there is no design provision for fixing a cub-board in the wall in side dining hall. | considered
52 | Kitchen entry/place for keeping the fridge/roof design on top of the kitchen entrance are at all not good. | considered
53 | Positioning of Commodes and wash basins in some of the bathrooms need review & repositioning so as to make more area for bathing/ for fitting bath curtains / fixing bath tub etc | considered
54 | The big window in the main bed room is found up to the floor level which is not liked by many. | considered
55 | Fan position in one of the bed room is not correct and found in front of the cub-board space. | considered
56 | Provision for CFL lighting not provided in all rooms. |  |  |  | Fittings are not in the provision of contract.
57 | TV cable plugs point not given in all rooms. | considered
58 | Windows grill design is plain and is not attractive and some of the grill bars fitted in the windows are found bend. |  |  |  | Same grille design will be followed with improved and sturdier rods and Flats.

## TYPE -A-II
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR TYPE 'A-II'
Ser No | Point | Without Financial Effect | With Fin Effect | Not Feasible | Remarks
1 | There should be one partition between the living room and dining hall. | Not considered
2 | In the front drawing room and both bedroom there is no proper ventilation it may be looked into. | Considered
3 | Provision for A/C be provided |  |  |  | Provision for split A/C already exists
4 | Provision of one wash basin for the dining hall be provided. | Not considered
5 | Wash basin with mirror and stand required./ wash basin in bath room is in front of window requires shifting |  |  |  | There is wide choice for allottees in the Market.
6 | Provide sufficient space for double cot bed provision. |  |  |  | Already Provisioned
7 | In the bed room the window could be extended to place a cub- board./ No provision for cup boards | Considered
8 | The plinth area can be increased by extending/ shifting the grill by another 10 feet to outer edge of both walls by which the main hall plinth area will be increased by 90 Sq Ft. |  | Refer Sl no.27 | Full area not Feasible | Due to DTCP norms and limitations
9 | There is no balcony in two bedrooms. Shifting (fitting) the window by another 2 ft gives an additional area of 6 sq ft in each bed room. |  |  | Not Feasible | Due to DTCP norms and limitations
10 | At least two more lofts is required in all three bed rooms. |  |  |  | Loftsare provided wherever it is possible in the bed room
11 | Separate transparent polycrol rectangular tank can be fitted in kitchen to have additional water facility. | Not considered
12 | There should be at least four 15 Amps plug points to fit Acquaguard /mixie/grinder and one spare in the kitchen. |  |  |  | Minimum .three 5amps & two 15 Amps. Provision Already exists
13 | Platform should be available in both sides in kitchen. |  |  |  | Provision only on one side. Other side for storage purpose
14 | The entrance side there should be a aloft which can be opened from inside to keep empty boxes. |  |  | Not Feasible | Due to Structural limitations
15 | The main door should be broad enough to take a big fridge inside the house and to plan to extend the kitchen to accommodate fridge | considered
16 | Extra dummy switches to be provided with the plug points to connect the UPS during power cuts. | Every switch board has a plug point. |  |  | Provision already exists for UPS
17 | Two additional 5 Amps plug point required in all switch boards. |  |  |  | Main switch board in each room will have one plug point provision.
18 | Provision to be made for bath tub fixing so that taps and mixtures to be fixed | Not considered |  |  | individual choice
19 | Wash Area to be little bigger |  |  | Not Feasible | Adequate space already provided
20 | Dining Room Window may be removed by making space for sit out/balcony | considered
21 | Study Room windows size to be increased. |  |  | Not Feasible
22 | Common gas pipe line to be provided |  |  |  | Provision already exist
23 | Utility space is too small does not serve the intended purpose |  |  |  | Appropriate size is provided
24 | Kitchen balcony can be extended to connect the balcony of the next bed room |  |  | Not Feasible | Due to DTCP norms and limitations
25 | All grills to be positioned on the outer side of the window. All windows can be positioned on the outer wall instead of inside. Mosquito proofing can be considered if not already included | Not considered
26 | Provision of space for washing machine, dish washer near a wash basin should be provided in the area near one bathroom along with the inlet/outlet plumbing. | Considered.
27 | a) There is no provision for dry cloths. One may be created by extending the balcony into the open space between the next house b) If all agree the wide window in the dining room can be shifted a fit out side. So that more space will be available. |  | Partly Considered the Extension of balcony (balcony and hand rail extra) Additional cost of approx of Rs 16000/ per unit
28 | The passage to common bedroom is very small needs to be increased. | Considered
29 | Kitchen wall adjacent to the bed rooms varies from the plan. The wall can come ,out adjacent to the door | Considered |  |  | .
30 | Drain trap can be upgraded with the Insect trap. |  |  |  | Provision already exists
31 | One of the toilets can be Indian type. (Presently all are in western type). | Not considered
32 | One of the bath room could be made low roof and roof space may be utilized for storage |  |  | Not feasible | Due to sunken slab no adequate height
33 | The extra platform (of approximate three inches height) on floor on the side of kitchen serves no utility and can be removed | Considered
34 | Master bed room need for more storage space. Wall next to windows can be used by widening the size of window by half. | Considered
35 | Provision of solar thermal power |  |  | Not Feasible | Usage limitations
36 | Service area balcony to be connected to other balcony. |  |  | Not possible | Due to DTCP norms and limitations
37 | Deviation for 2nd bedroom (Access to bathroom from bedroom not from dining room) as done in model flat. | considered
38 | Interchange of toilet and wash basin in the second bedroom Toilet should be one side and wash basin could be in centre | Considered
39 | Need to provide a wash outlet and tap near iron grill can be done on common area. (Adjacent to door) as it will be easy to clean the area. | Not considered
40 | The wall are constructed with solid blocks which is not good compared to to clay bricks. Use of rock antics similar to Jalvayuvihar (Bangalore) could be through off. |  |  |  | The sold blocks are as per IS specification and the quality has been ensured by PD doing the periodical laboratory test.
41 | Kitchen size is extremely small with no storage space. Suggested to use area in front of second attached bedroom space for kitchen. | Considered
42 | There is wastage of space in front of bed room adjacent to study room and there is a sharp turn which may prevent mounting in of pre assembled COT/CUPBOARDS. | Considered |  |  | Adequate space provided now

## TYPE -A-III
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR TYPE 'A-III'
Sl.No | Point | Without Financial Effect | With Financial Effect | Not Feasible | Remarks
1 | The colour of vitrified tiles and bathroom tiles can be of lighter shade (off white). | Considered.
2 | Kitchen wall tiles area may be increased. |  |  | Not feasible
3 | The curtain of steel rod may be provided. | Not considered.
4 | Separate water tank for each house may be provided. |  |  | Not feasible
5 | Window grills gap to be reduced. Grill quality is poor. | Considered.
6 | Balcony area may be increased. |  |  | Not Feasible | DTCP norms
7 | Separate meter for water/electricity/gas may be provided. |  |  |  | Separate meter for EB & Gas, will be as per the department’s charges at time of possession by individual. However Common water meter will be organized by society
8 | Standby power supply to each house to be provided. |  | 0.5 KVA- Rs.15000/- Per unit (approx) |  | .
9 | Molding should be contemporary design. | Considered.
10 | 15 Amp point for refrigerator may be provided. |  |  |  | 5 Amp is sufficient for refrigerator.
11 | Provision for wall mounted LCD in living may be provided. |  |  |  | Provision for TV point is already exists.
12 | Provision for cable TV or dish TV may be provided. | considered
13 | Mosquito mesh door provision not for Velcro nets but movable mesh screens. |  |  |  | Provision already exists for all the windows except kitchen window
14 | Black galaxy granite may be provided in Kitchen |  |  |  | Present proposed cats eye granite is expensive than the black granite
15 | Ledge on left side to be removed at floor level. | considered
16 | Ledge below counter to be removed if causeways arrived at. In any case provision to accommodate cylinder below counter. | considered |  |  | Sill below the Kitchen platform is deleted.
17 | Wash area to have a side slab. | considered
18 | Switch design, position and finish not desirable may be improved. | Considered.
19 | Relocate entrance switch, if not relocate wardrobe position i.e relocate window | considered
20 | Bed position is altered to colour wall which is behind bed. | considered
21 | Shift WC position to the centre of door and ledge wall behind WC to go to end wall. |  |  | Not feasible | Counter top wash basin being considered
22 | Provide counter ledge for Wash basin | Considered |  |  | Provision already exists.
23 | Increase size of ventilation of common bathroom. |  |  |  | Adequate ventilation is provided
24 | Provision for split A/C to be provided in all rooms. |  |  |  | In all bedrooms Provision already Exists
25 | Independent water tanks for each apartment may be provisioned. |  |  | Not Feasible. | Individual choice
26 | Additional area available across the road to be used to amenities like parking and shops | In consideration |  |  | A proposal for the vacant land is been worked out
27 | Provision of grill for balconies for ensuring safety may be provided. |  |  | Not Feasible
28 | The power point provisioned for fridge is blocking the pathway. This may be re located | Considered
29 | The window in the master toilet is low. This may be positioned bit more above. | Not considered |  |  | Most of the allottees have preferred as of present status.

## TYPE -B
APPENDIX-'A'
POINTS RAISED BY ALLOTTEES DURING ALLOTTEES MEETING HELD ON 01 MAY 11 FOR TYPE 'B'
Sl.No | Point | Without Financial Effect | With Financial Effect | Not Feasible | Remarks
1 | Mosquito mesh / Wire mesh to be included in all windows. |  |  |  | Provisions already exists except Kitchen window
2 | Cradle Hooks to be provided in bed rooms . |  | Considered at the extra cost Rs 500 per hook
3 | Locks to be changed | considered
4 | In kitchen beneath the plate form height may not be sufficient . | considered
5 | Hall and dining room are almost the same and there is no space to fix TV in wall. |  |  |  | Propvision for TV is already in the Drg/Dini hall.
6 | Provision for a pooja room may be provided. |  |  | Not feasible
7 | Provide two piped dummy hole for AC |  |  |  | Suitable hole may be done by the A/C supplier during the Installation
8 | Please provide one Indian Style toilet which is in common area. | Not considered
9 | The WC in the toilet to be moved to one side of the bathroom | considered
10 | UPS wiring points to be identified and marked accordingly. |  |  |  | Provision already exists
11 | Required an additional wash basin in utility area dining hall. | Not considered
12 | Windows grill must be out side and window glasses should be inside. Gap minimized for security reasons | Not considered
13 | Gas connecting point for cylinder required in kitchen |  |  |  | Provision already exists
14 | Bottom base under table top in kitchen not required extra area can be used for utensils. | considered
15 | In kitchen over the table top, tiles ht may be increased. |  |  | Not Feasible | For future wall unit provision
16 | Provision required for cloth drying hooks in balconies and utility area. | Not considered |  |  | There is wide choice for allottees in the Market.
17 | Towel hanging rod ,mirror and soap case in bathrooms to be provided | Not considered |  |  | There is wide choice for allottees in the Market.
18 | Solar water heater provision required |  |  | Not Feasible | Usage of limitations
19 | Kitchen kadappa slab is only 9 inches. Need to be bigger to keep utensils. | considered
20 | A show case provision may be provided in hall |  |  |  | Individual choice
21 | Additional store room may be made near toilet | Common loft provided now. |  |  | Not feasible to provide one Room for store
22 | Extra iron grill door can be given to iron door for safety. |  |  |  | Not required as Main door is steel door.
23 | Storage can be made in the place provided before the common toilets | considered |  |  | .
24 | Balcony dimension may be increased than the planned dimension along with the grill provided for the safety upto the roof |  |  | Not feasible- | (DTCP norms)Limitation
25 | Eye lens to be placed in the front door. |  |  |  | Provision already exists
26 | T bolt in the front door |  |  |  | Provision already exists
27 | Stainless Sink size to be increased | considered
28 | 15 Amps socket to be provided in Kitchen. |  |  |  | Provision already exists
29 | Door may be provided for kitchen. |  |  | Not feasible | For safety norms
30 | Iron table / writing table may be provided in any of the bed room. |  |  |  | Individual choice
31 | Ventilator exhaust fan may be provided in both bedroom toilet |  |  |  | Provision already exists
32 | Additional TV point to be provided on the entrance room opposite to main door near sit out. |  |  |  | Provided in appropriate location
33 | Kitchen slabs on one side to be removed to cater more space for usage | Shelf slabs provisioned |  |  | Cuddapah slab provided only for storage
34 | Metal shade on balcony and sit out to be fitted with angle facing outward to avoid water coming inside. |  |  | Not Feasible | It will not match the elevation
35 | Provision of phone line point in drawing room may be provided. |  |  |  | Provision already exists
36 | Tap point may be given at a higher level at service place beside kitchen and plug point for washing machine |  |  |  | Provision already exists
37 | Position of sink can be changed in kitchen | Considered
38 | Living room wall near toilet can be avoided so as to provided space for keeping refrigerator |  |  |  | Keeping for refrigerator,provision is exists In the hall